## 12-Week Plan
Java Full Stack: 12-Week Revision and Deep-Dive Plan (DSA tracked separately)
Rule: finish the deliverable before moving on, then write a one-page 'how I would explain this in an interview' note.
Weeks done | 0 |  | Hours planned | 240
Progress | 0% |  | Hours done | 0
Week | Focus | Deep-dive topics | Tied to | Deliverable | Status | Hours planned | Hours done | Notes
1-2 | Core Java internals | JVM memory and GC, HashMap and collections internals, concurrency, memory model, streams | Core Java guide, Parts 6-9 | Explain HashMap, GC and the memory model without notes; revision notes written | Not started | 40 | 0
3-4 | Spring internals | IoC and bean lifecycle, proxies and AOP, auto-configuration; @Transactional propagation and isolation pitfalls; JPA N+1, locking, lazy loading; Security filter chain, JWT refresh and revocation | Swagruha Food, internship project | Fix one real N+1 and one transaction bug in a project; explain the filter chain | Not started | 40 | 0
5 | Databases and Redis | Indexes and query plans, isolation levels, MVCC, locking; Redis data structures, persistence, eviction, cache patterns, cache stampede | CareerFlux | Index one slow CareerFlux query with before/after timings; cache-stampede test | Not started | 20 | 0
6-7 | Kafka deep dive | Partitions, consumer groups, offsets, delivery semantics, idempotent producers, transactions, dead-letter queues, ordering; RabbitMQ vs Kafka | CareerFlux pipeline | Duplicate-delivery test and DLQ added to the pipeline; one-page design note | Not started | 40 | 0
8-9 | Distributed systems and system design | CAP and consistency models, Raft in depth, replication, idempotency, retries, circuit breakers, sagas; 8-10 system design problems | Distributed key-value store | 3-minute Raft explanation; 8-10 designs written up | Not started | 40 | 0
10 | React deep dive and testing | Rendering, hooks, performance, state management, TypeScript; JUnit, Mockito, Testcontainers | Nexus AI, Swagruha Food | Tests added to one backend project; one React performance fix | Not started | 20 | 0
11 | Docker, CI/CD and cloud | Docker in depth, GitHub Actions CI/CD, AWS deployment, logging and monitoring | CareerFlux | CareerFlux live on a public URL with CI running | Not started | 20 | 0
12 | Resume, rehearsal and applications | Resume rewrite, 3-minute architecture walkthrough for each project, mock interviews, apply | All projects | Resume final; 5+ mock interviews done; applications sent | Not started | 20 | 0
Legend: yellow cells are yours to edit (Status, Hours done, Notes). Blue numbers are planned hours (assumption: about 20 h/week; change if your pace differs). Example note: 'Raft: re-read log replication, still unsure about commit index'.

## Resume Fixes
# | Issue | Fix | Priority | Status
1 | Internship title is cut off ('Online Medication and p') | Correct the title and project name in the Infosys Springboard line | High | Open
2 | No measurable results | Add honest numbers: requests/second, latency before/after caching, node count, events processed; measure a few if missing | High | Open
3 | No live links on projects | Add demo and GitHub links; deploy at least CareerFlux | High | Open
4 | Missing keywords: testing, CI/CD, cloud | Add JUnit/Mockito, GitHub Actions and AWS only after actually using them | High | Open
5 | Generic summary | Use a concrete line: Java backend and full stack developer; built Kafka pipelines, a Raft-based store and JWT-secured APIs | Medium | Open
6 | RabbitMQ listed in skills but used in no project | Use it in one project or remove it | Medium | Open
7 | Formatting: missing space in 'PostgreSQL,Redis' | Fix spacing | Low | Open
| Fixes done | 0 of 7

## Project Interview Prep
Project | Topic to defend | Questions to be ready for | Prepared?
Distributed Key-Value Store | Raft | Leader election, log replication, behaviour in a network partition, commit rules, what happens when the leader fails | No
CareerFlux | Kafka pipeline | Why Kafka, partitioning key, consumer groups, duplicate events, delivery guarantees, failure and retry handling | No
CareerFlux | Redis and PostgreSQL | What is cached and why, eviction and invalidation, cache stampede, indexing choices | No
Swagruha Food | Spring Security and JWT | Filter chain, token storage, refresh and revocation, role-based access | No
Internship project (medication tracker) | Layering and validation | Why thin controllers, where validation lives, transaction boundaries, API error handling | No
Nexus AI | LLM integration | Architecture, how retrieval works, security of API keys and data, failure handling | No
All projects | 3-minute walkthrough | Architecture, your role, hardest bug, what you would change | No
|  | Ready ('Yes') | 0 of 7