## Day by Day
Day-by-Day Plan: 8 Weeks, Mon 26 Oct 2026 to Sun 20 Dec 2026
Rule: a day is Done only when its output exists. Minutes are a planning assumption (weekday 150, Saturday 300, Sunday 150).
Start date (Monday) |  | 2026-10-26 |  | Days done | 0 of 56 |  | Hours done | 0.5
|  |  |  | Hours planned | 160
Day | Date | Weekday | Week | Theme | Study chapters (guide, part, chapters) | Hours | Study min | Build or hands-on min | DSA task | DSA min | Review or output min | Done when (output) | Total min | Status | Hours done | Notes
1 | 2026-10-26 | Mon | 1 | Core Java: OOP, collections and streams | Core Java Part 3 (Object-Oriented Java): Inheritance; Polymorphism and Dynamic Dispatch; Abstract Classes and Interfaces | 2.5 | 60 | 30 | DSA Patterns Part 1: Complexity analysis; Java toolkit for DSA (read both, then solve 1 easy problem) | 45 | 15 | Explain abstract class versus interface in 2 minutes, aloud. | 150 | started | 0.5
2 | 2026-10-27 | Tue | 1 | Core Java: OOP, collections and streams | Core Java Part 3: The Object Class; Wrapper Classes, Autoboxing and Identity. Part 4: Strings in depth | 2.5 | 60 | 30 | DSA Patterns: Prefix Sum and Difference Array. 2 problems | 45 | 15 | equals and hashCode written for one class and tested in a HashSet. | 150 | Not started | 0
3 | 2026-10-28 | Wed | 1 | Core Java: OOP, collections and streams | Core Java Part 6 (Generics and Collections): The Collections Framework; Lists in depth; Sets | 2.5 | 60 | 30 | DSA Patterns: Two Pointers. 2 problems | 45 | 15 | Table of ArrayList, LinkedList, HashSet and TreeSet with Big-O, written from memory. | 150 | Not started | 0
4 | 2026-10-29 | Thu | 1 | Core Java: OOP, collections and streams | Core Java Part 6: HashMap in depth; Other maps: LinkedHashMap, TreeMap and the specialists; Choosing a data structure, and Big-O | 2.5 | 60 | 30 | DSA Patterns: Sliding Window: Fixed Size. 2 problems | 45 | 15 | 3-minute HashMap explanation covering hashing, resize and treeification. | 150 | Not started | 0
5 | 2026-10-30 | Fri | 1 | Core Java: OOP, collections and streams | Core Java Part 5: Exceptions. Part 6: Generics | 2.5 | 60 | 30 | DSA Patterns: Sliding Window: Variable Size. 2 problems | 45 | 15 | One-page note on checked versus unchecked exceptions and wildcard generics. | 150 | Not started | 0
6 | 2026-10-31 | Sat | 1 | Core Java: OOP, collections and streams | Core Java Part 6: Implement your own: array list, linked list, hash map, LRU cache. Part 7 (Functional Java): Lambdas and Functional Interfaces; Streams: Fundamentals; Collectors | 5 | 120 | 90 | DSA Patterns: Hash Map and Frequency Counting. 3 problems | 60 | 30 | Own HashMap and LRU cache coded and tested; 5 stream pipelines written. | 300 | Not started | 0
7 | 2026-11-01 | Sun | 1 | Core Java: OOP, collections and streams | Core Java Part 14 (Interview Preparation): Interview Q&A: Language, OOP, Strings, Exceptions and I/O; Interview Q&A: Collections, Generics, Streams and Functional Java | 2.5 | 75 | 0 | Redo any two problems left unsolved this week | 45 | 30 | Weekly review: questions that could not be answered are listed in the Notes column. | 150 | Not started | 0
8 | 2026-11-02 | Mon | 2 | Concurrency, the JVM and Spring internals | Core Java Part 8 (Concurrency): Concurrency Concepts; Threads; Races and the Java Memory Model | 2.5 | 60 | 30 | DSA Patterns: Binary search on sorted arrays. 2 problems | 45 | 15 | Race condition reproduced with two threads and a shared counter. | 150 | Not started | 0
9 | 2026-11-03 | Tue | 2 | Concurrency, the JVM and Spring internals | Core Java Part 8: synchronized and Monitors; Locks and Atomics; Thread Confinement, Immutability and Liveness | 2.5 | 60 | 30 | DSA Patterns: Binary search on the answer. 2 problems | 45 | 15 | Deadlock written, then fixed with lock ordering. | 150 | Not started | 0
10 | 2026-11-04 | Wed | 2 | Concurrency, the JVM and Spring internals | Core Java Part 8: Executors and Thread Pools; CompletableFuture; Synchronizers and Concurrent Collections | 2.5 | 60 | 30 | DSA Patterns: Sorting-based problems and merge intervals. 2 problems | 45 | 15 | Small ExecutorService program that runs 3 tasks in parallel with a timeout. | 150 | Not started | 0
11 | 2026-11-05 | Thu | 2 | Concurrency, the JVM and Spring internals | Core Java Part 9 (The JVM in Depth): Objects in Memory; Heap Structure and Reference Types; Garbage Collection Fundamentals; The Collectors | 2.5 | 60 | 30 | DSA Patterns: Kadane, greedy scans and in-place array tricks. 2 problems | 45 | 15 | Heap, stack and metaspace drawn from memory; phases of the G1 collector listed. | 150 | Not started | 0
12 | 2026-11-06 | Fri | 2 | Concurrency, the JVM and Spring internals | Core Java Part 9: Reading GC Logs and Tuning; Memory Leaks and OutOfMemoryError. Part 8: Virtual Threads | 2.5 | 60 | 30 | DSA Patterns: Linked list basics, dummy node and reversal. 2 problems | 45 | 15 | OutOfMemoryError reproduced and diagnosed with jcmd or a heap dump. | 150 | Not started | 0
13 | 2026-11-07 | Sat | 2 | Concurrency, the JVM and Spring internals | Spring Boot Basics Part 1 (Spring Boot Foundations): all five chapters. Spring Boot Beyond Basics Part 1: The Spring Container Internals; AOP and Proxies | 5 | 120 | 90 | DSA Patterns: Fast and slow pointers. 3 problems | 60 | 30 | Bean lifecycle and proxy diagram drawn from memory; 2-minute explanation of how @Transactional works through a proxy. | 300 | Not started | 0
14 | 2026-11-08 | Sun | 2 | Concurrency, the JVM and Spring internals | Core Java Part 14: Interview Q&A: Concurrency, the Memory Model and the JVM; Interview Q&A: Modern Java; What Does This Print? Fifty Puzzles (first 25) | 2.5 | 75 | 0 | Redo any two problems left unsolved this week | 45 | 30 | Weekly review: weak topics noted in the Notes column. | 150 | Not started | 0
15 | 2026-11-09 | Mon | 3 | Spring data access, transactions and security | Spring Boot Beyond Basics Part 1: Auto-Configuration and Configuration in Depth; The Spring MVC Request Lifecycle | 2.5 | 60 | 30 | DSA Patterns: Stack patterns. 2 problems | 45 | 15 | Request path from DispatcherServlet to response drawn from memory. | 150 | Not started | 0
16 | 2026-11-10 | Tue | 3 | Spring data access, transactions and security | Spring Boot Beyond Basics Part 2 (Data Access in Depth): JPA and Hibernate Architecture; Mapping in Depth | 2.5 | 60 | 30 | DSA Patterns: Monotonic stack. 2 problems | 45 | 15 | Persistence context and entity states explained in 3 minutes. | 150 | Not started | 0
17 | 2026-11-11 | Wed | 3 | Spring data access, transactions and security | Spring Boot Beyond Basics Part 2: Fetching and the N+1 Family; Performance of the Data Layer | 2.5 | 60 | 30 | DSA Patterns: Queue, deque and monotonic deque. 2 problems | 45 | 15 | A real N+1 reproduced and fixed in Swagruha Food or the internship project, with query counts before and after. | 150 | Not started | 0
18 | 2026-11-12 | Thu | 3 | Spring data access, transactions and security | Spring Boot Beyond Basics Part 2: Transactions in Spring; Query Techniques and Spring Data Internals | 2.5 | 60 | 30 | DSA Patterns: Recursion and Divide and Conquer. 2 problems | 45 | 15 | A test that shows the self-invocation @Transactional pitfall; table of propagation and isolation written. | 150 | Not started | 0
19 | 2026-11-13 | Fri | 3 | Spring data access, transactions and security | Spring Boot Beyond Basics Part 3 (Spring Security): Security Architecture: Filters, Authentication and Password Storage; Authorisation: Request Rules, Method Security and Ownership | 2.5 | 60 | 30 | DSA Patterns: Backtracking: Subsets, Permutations, Combinations. 2 problems | 45 | 15 | Security filter chain explained from memory. | 150 | Not started | 0
20 | 2026-11-14 | Sat | 3 | Spring data access, transactions and security | Spring Boot Beyond Basics Part 3: Web Attacks and Defences; Sessions and Tokens: Choosing an Authentication State Model; JSON Web Tokens in Depth; OAuth 2.0 and OpenID Connect; Securing Microservices and Testing Security | 5 | 120 | 90 | DSA Patterns: Backtracking on Grids and Constraints. 3 problems | 60 | 30 | JWT refresh and revocation design implemented in Swagruha Food, with a one-page note. | 300 | Not started | 0
21 | 2026-11-15 | Sun | 3 | Spring data access, transactions and security | Spring Boot Beyond Basics Part 5: Testing Strategy and Unit Tests; Spring Slice Tests and Context Caching; Integration Testing with Testcontainers. Spring Boot Basics Part 6: Interview Q&A | 2.5 | 75 | 0 | Redo any two problems left unsolved this week | 45 | 30 | Tests added to one backend project (service unit tests plus one @DataJpaTest or Testcontainers test). | 150 | Not started | 0
22 | 2026-11-16 | Mon | 4 | Databases and Redis | Databases Part 1 (Relational): SQL Fundamentals; Joins; Aggregation and Grouping; Subqueries and Common Table Expressions | 2.5 | 60 | 30 | DSA Patterns: Binary Tree DFS. 2 problems | 45 | 15 | 10 SQL queries written without looking; start the SQL Practice Plan tab. | 150 | Not started | 0
23 | 2026-11-17 | Tue | 4 | Databases and Redis | Databases Part 1: Window Functions; Thirty Classic SQL Interview Problems (first 15) | 2.5 | 60 | 30 | DSA Patterns: Binary Tree BFS and Level Order. 2 problems | 45 | 15 | 15 SQL problems solved and timed. | 150 | Not started | 0
24 | 2026-11-18 | Wed | 4 | Databases and Redis | Databases Part 1: Indexes; Reading Query Plans; Query Optimisation Techniques; Slow Query Diagnosis | 2.5 | 60 | 30 | DSA Patterns: BST and Tree Construction. 2 problems | 45 | 15 | One slow CareerFlux query indexed, with EXPLAIN output and timings before and after. | 150 | Not started | 0
25 | 2026-11-19 | Thu | 4 | Databases and Redis | Databases Part 1: Transactions and ACID; Concurrency Anomalies and Isolation Levels; MVCC Internals, VACUUM and Bloat; Locking, Deadlocks and Optimistic Concurrency | 2.5 | 60 | 30 | DSA Patterns: Tries. 2 problems | 45 | 15 | Isolation level and anomaly table written from memory. | 150 | Not started | 0
26 | 2026-11-20 | Fri | 4 | Databases and Redis | Redis Part 1: What Redis Is; Why Redis Is Fast. Part 3 (Data Structures): Strings; Hashes; Sets; Sorted sets; Choosing the right structure. Part 4: Expiration; Memory Limits and Eviction | 2.5 | 60 | 30 | DSA Patterns: Heaps and Top-K. 2 problems | 45 | 15 | Redis structure chosen for a session, a leaderboard, unique visitors and a queue, each answered with the commands. | 150 | Not started | 0
27 | 2026-11-21 | Sat | 4 | Databases and Redis | Redis Part 8 (Patterns): Caching fundamentals; Cache-aside; Cache failure modes; Distributed locks; Rate limiting. Part 7: Spring Cache with Redis | 5 | 120 | 90 | DSA Patterns: Graph Representation, DFS and BFS. 3 problems | 60 | 30 | Cache-stampede test on CareerFlux with a mitigation (lock or jitter); results noted. | 300 | Not started | 0
28 | 2026-11-22 | Sun | 4 | Databases and Redis | Databases Part 2 (NoSQL): Why NoSQL; Distributed data fundamentals; Choosing a database; Relational versus Non-Relational: A Head-to-Head Comparison; Interview Question Bank | 2.5 | 75 | 0 | Redo any two problems left unsolved this week | 45 | 30 | Weekly review; the choice of SQL versus NoSQL for CareerFlux explained in 2 minutes. | 150 | Not started | 0
29 | 2026-11-23 | Mon | 5 | Operating systems and computer networks | Operating Systems Part 2 (Processes, Threads and Scheduling): Processes; Threads; CPU Scheduling | 2.5 | 60 | 30 | DSA Patterns: Topological Sort. 2 problems | 45 | 15 | Process versus thread comparison from memory; cost of a context switch explained. | 150 | Not started | 0
30 | 2026-11-24 | Tue | 5 | Operating systems and computer networks | Operating Systems Part 3 (Memory Management): Virtual Memory and Address Spaces; Paging and Address Translation; Page Replacement, Working Sets and Swapping; The Memory of a JVM Process | 2.5 | 60 | 30 | DSA Patterns: Union-Find (Disjoint Set Union). 2 problems | 45 | 15 | Virtual-to-physical address translation worked on paper for a small example. | 150 | Not started | 0
31 | 2026-11-25 | Wed | 5 | Operating systems and computer networks | Operating Systems Part 4 (Concurrency and Synchronisation): Race Conditions and Critical Sections; Mutexes, Semaphores, Condition Variables and Spinlocks; Deadlock, Livelock, Starvation and Priority Inversion | 2.5 | 60 | 30 | DSA Patterns: Shortest Paths. 2 problems | 45 | 15 | Four deadlock conditions and a prevention for each, written from memory. | 150 | Not started | 0
32 | 2026-11-26 | Thu | 5 | Operating systems and computer networks | Computer Networks Part 1 and 2: Layered Architecture; IPv4 Addressing and the IPv4 Header; Classless Addressing and Subnetting. Part 3: TCP Segments and Connection Management; TCP Reliability | 2.5 | 60 | 30 | DSA Patterns: Dynamic programming: the method. 2 problems | 45 | 15 | Three subnetting problems solved; three-way handshake drawn. | 150 | Not started | 0
33 | 2026-11-27 | Fri | 5 | Operating systems and computer networks | Computer Networks Part 3 and 4: Flow Control; Congestion Control; The Domain Name System; HTTP/1.1; HTTP Caching and Conditional Requests | 2.5 | 60 | 30 | DSA Patterns: DP on grids and paths. 2 problems | 45 | 15 | DNS resolution steps and HTTP caching headers explained. | 150 | Not started | 0
34 | 2026-11-28 | Sat | 5 | Operating systems and computer networks | Computer Networks Part 4 to 6: Cookies, Sessions and Authentication over HTTP; HTTP/2 and HTTP/3; Cross-Origin Resource Sharing (CORS); TLS and HTTPS; Reverse Proxies, Load Balancers and Gateways; What Happens When a URL Is Entered | 5 | 120 | 90 | DSA Patterns: Knapsack patterns. 3 problems | 60 | 30 | 5-minute spoken walkthrough of what happens when a URL is entered, recorded. | 300 | Not started | 0
35 | 2026-11-29 | Sun | 5 | Operating systems and computer networks | Operating Systems Part 6: Interview Question Bank. Computer Networks Part 6: Interview Question Bank | 2.5 | 75 | 0 | Redo any two problems left unsolved this week | 45 | 30 | Weekly review; list of weak topics in the Notes column. | 150 | Not started | 0
36 | 2026-11-30 | Mon | 6 | System design, microservices and Kafka | System Design Part 1: How to Approach a System Design Interview; Back-of-the-Envelope Estimation; Scalability and Performance Basics | 2.5 | 60 | 30 | DSA Patterns: DP on strings and sequences. 2 problems | 45 | 15 | One estimation worked on paper (QPS, storage, bandwidth). | 150 | Not started | 0
37 | 2026-12-01 | Tue | 6 | System design, microservices and Kafka | System Design Part 1: Load Balancing and Networking for Design; Availability and Reliability; Choosing the Data Store; Caching | 2.5 | 60 | 30 | DSA Patterns: DP on intervals, trees and states. 2 problems | 45 | 15 | Cache strategies (aside, read-through, write-back) compared in a table from memory. | 150 | Not started | 0
38 | 2026-12-02 | Wed | 6 | System design, microservices and Kafka | System Design Part 1: Replication, Partitioning and Consistent Hashing; Consistency and Distributed Coordination; Asynchronous Processing and Messaging; Common Infrastructure Components | 2.5 | 60 | 30 | DSA Patterns: Greedy. 2 problems | 45 | 15 | Consistent hashing explained in 3 minutes. | 150 | Not started | 0
39 | 2026-12-03 | Thu | 6 | System design, microservices and Kafka | System Design Part 2 (High-Level Design Case Studies): Design: URL Shortener; Design: Distributed Rate Limiter; Design: Unique ID Generator | 2.5 | 60 | 30 | DSA Patterns: Bit manipulation. 2 problems | 45 | 15 | Two designs done on paper in 35 minutes each, then compared with the chapter. | 150 | Not started | 0
40 | 2026-12-04 | Fri | 6 | System design, microservices and Kafka | System Design Part 2: Design: News Feed; Design: Chat System; Design: Notification System | 2.5 | 60 | 30 | DSA Patterns: Pattern recognition cheat sheet (read), then 2 problems | 45 | 15 | One design done on paper in 35 minutes. | 150 | Not started | 0
41 | 2026-12-05 | Sat | 6 | System design, microservices and Kafka | Spring Boot Beyond Basics Part 4 (Microservices and Resilience): Microservice Architecture; Synchronous Communication; Service Discovery, Configuration and Gateways; Resilience: Timeouts, Retries, Circuit Breakers and Bulkheads; Distributed Data and Transactions. Kafka Part 1: What Kafka Is (and What It Is Not); The Building Blocks at a Glance; What Kafka Guarantees. Part 2: Topics, Partitions and the Commit Log | 5 | 120 | 90 | DSA Patterns: Mixed interview questions. 3 problems | 60 | 30 | Timeout, retry and circuit breaker each explained with the failure it prevents. | 300 | Not started | 0
42 | 2026-12-06 | Sun | 6 | System design, microservices and Kafka | Kafka Part 3: Reliability: Acknowledgements, Retries and Idempotence. Part 6: Error Handling in Spring Kafka Listeners; Non-Blocking Retries with @RetryableTopic; Idempotent Consumers and the Inbox Pattern. System Design Part 1: Asynchronous Processing and Messaging (consumer groups and delivery semantics) | 2.5 | 75 | 0 | Redo any two problems left unsolved this week | 45 | 30 | Duplicate-delivery test and a dead-letter topic added to the CareerFlux pipeline; one-page design note. | 150 | Not started | 0
43 | 2026-12-07 | Mon | 7 | Low-level design, Git, Docker and CI/CD | System Design Part 3 (Low-Level Design in Java): Object-Oriented Design Principles; Design Patterns for LLD; The LLD Interview Process | 2.5 | 60 | 30 | DSA Patterns: Mixed interview questions. 2 problems | 45 | 15 | Each SOLID principle stated with a one-line violation example. | 150 | Not started | 0
44 | 2026-12-08 | Tue | 7 | Low-level design, Git, Docker and CI/CD | System Design Part 3: LLD: Parking Lot; LLD: LRU and LFU Cache; LLD: Elevator System | 2.5 | 60 | 30 | DSA Patterns: Mixed interview questions. 2 problems | 45 | 15 | Parking Lot coded from scratch in 45 minutes without looking. | 150 | Not started | 0
45 | 2026-12-09 | Wed | 7 | Low-level design, Git, Docker and CI/CD | System Design Part 3: LLD: Splitwise, Expense Sharing; LLD: Vending Machine; LLD: Rate Limiter; LLD: Movie Ticket Booking, Seat Hold | 2.5 | 60 | 30 | DSA Patterns: Mixed interview questions. 2 problems | 45 | 15 | Seat-hold race condition reproduced and fixed. | 150 | Not started | 0
46 | 2026-12-10 | Thu | 7 | Low-level design, Git, Docker and CI/CD | Git, Docker and CI/CD Part 1 (Git and GitHub): Version Control and How Git Stores Data; Everyday Git; Branching, Merging and Rebasing; Recovering from Mistakes | 2.5 | 60 | 30 | DSA Patterns: Mixed interview questions. 2 problems | 45 | 15 | A merge conflict resolved and a deleted branch recovered with the reflog, on a practice repository. | 150 | Not started | 0
47 | 2026-12-11 | Fri | 7 | Low-level design, Git, Docker and CI/CD | Git, Docker and CI/CD Part 1: Remotes and Collaboration; Branching Strategies and Team Workflows; GitHub. Part 2 (Containers with Docker): Containers, Namespaces and cgroups; Images and Layers; Writing Dockerfiles | 2.5 | 60 | 30 | DSA Patterns: Mixed interview questions. 2 problems | 45 | 15 | Branch protection and a pull request workflow set up on a personal repository. | 150 | Not started | 0
48 | 2026-12-12 | Sat | 7 | Low-level design, Git, Docker and CI/CD | Git, Docker and CI/CD Part 2: Dockerizing a Spring Boot Application; Docker Compose; Container Security and Image Hardening. Part 3 (Continuous Integration and Delivery): GitHub Actions Fundamentals; GitHub Actions: Matrices, Images, Environments and Reuse | 5 | 120 | 90 | DSA Patterns: Mixed interview questions. 3 problems | 60 | 30 | CareerFlux with a multi-stage Dockerfile, a Compose file (app, PostgreSQL, Redis) and a GitHub Actions workflow running green. | 300 | Not started | 0
49 | 2026-12-13 | Sun | 7 | Low-level design, Git, Docker and CI/CD | Git, Docker and CI/CD Part 3: Why Jenkins When GitHub Has Actions; The Jenkinsfile: Declarative Pipeline in Practice. Part 4: Deployment Strategies and Safe Releases | 2.5 | 75 | 0 | Redo any two problems left unsolved this week | 45 | 30 | Answer to why Jenkins is used when GitHub has Actions rehearsed in 2 minutes; weekly review. | 150 | Not started | 0
50 | 2026-12-14 | Mon | 8 | Deployment, resume, mocks and applications | Git, Docker and CI/CD Part 4 (Running in Production): Why Orchestration and Kubernetes Architecture; Core Objects: Pods, Deployments, Services and Configuration; Cloud Foundations and IAM; Running orders-service on AWS | 2.5 | 60 | 30 | DSA Patterns Part 7: Final checklist and how to practise on LeetCode. 2 problems | 45 | 15 | Deployment target for CareerFlux chosen (EC2 or ECS) and the steps written down. | 150 | Not started | 0
51 | 2026-12-15 | Tue | 8 | Deployment, resume, mocks and applications | Build day: deploy CareerFlux. Push the image to a registry and run it on the chosen AWS target behind a public URL. Reference: Git, Docker and CI/CD Part 4: Running orders-service on AWS; Secrets and Configuration | 2.5 | 120 | 0 | 2 timed problems (25 minutes each) | 30 | 0 | CareerFlux live on a public URL with CI running; link added to the README and the resume. | 150 | Not started | 0
52 | 2026-12-16 | Wed | 8 | Deployment, resume, mocks and applications | Resume and project walkthroughs: work through the Resume Fixes tab; prepare a 3-minute architecture walkthrough per project using the Project Interview Prep tab | 2.5 | 105 | 0 | 2 problems | 45 | 0 | Final resume; one walkthrough note per project. | 150 | Not started | 0
53 | 2026-12-17 | Thu | 8 | Deployment, resume, mocks and applications | Mock interview 1: Core Java and Spring Boot. Question sources: Core Java Part 14 and Spring Boot Beyond Basics Part 6: Interview Question Bank | 2.5 | 105 | 0 | 2 timed problems | 45 | 0 | Mock completed with a peer or recorded; weak answers listed. | 150 | Not started | 0
54 | 2026-12-18 | Fri | 8 | Deployment, resume, mocks and applications | Mock interview 2: Databases and System Design. Question sources: Databases Part 2: Interview Question Bank and System Design Part 4: Interview Preparation | 2.5 | 105 | 0 | 2 timed problems | 45 | 0 | Mock completed; one full high-level design presented in 40 minutes. | 150 | Not started | 0
55 | 2026-12-19 | Sat | 8 | Deployment, resume, mocks and applications | Mock interview 3: DSA (2 timed problems) and LLD (one machine-coding problem in 60 minutes). Then apply and polish the GitHub README and LinkedIn profile using the GitHub chapter in Git, Docker and CI/CD Part 1 | 5 | 240 | 0 | Two timed problems inside the mock | 60 | 0 | 15 applications sent with a tailored resume; profiles updated. | 300 | Not started | 0
56 | 2026-12-20 | Sun | 8 | Deployment, resume, mocks and applications | Final revision from the cheat sheets: System Design Part 4, Databases Part 2, Spring Boot Beyond Basics Part 6, Git, Docker and CI/CD Part 4 | 2.5 | 105 | 0 | Redo any unsolved problems | 45 | 0 | Next-phase plan written: about 10 applications and 1 mock interview per week. | 150 | Not started | 0
Legend: yellow cells are yours to edit (start date, Status, Hours done, Notes). Blue numbers are planned values and can be changed; Total min is checked against Hours (150 min = 2.5 h, 300 min = 5 h). Example note: 'Isolation levels: still unsure when a phantom read occurs'.
Formulas:
Date = C4+[Day]-1